## Jira Backlog
Issue ID | Issue Type | Summary | Description | Story Points | Assigned To | Branch Name | Status
QA-0 | Epic | Project Documentations | Project Documentations SRS, Presentation, Jira, Final Report | 2 | Pawan Sharma | document-setup | To Do
QA-1 | Epic | Project Setup & Architecture | Initial project setup with folder structure and dependencies | 5 | Pawan Sharma | feature/project-setup | To Do
QA-2 | Story | Flask App Initialization | Create Flask app with base routes | 3 | Adrash | feature/flask-init | To Do
QA-3 | Story | Frontend UI Development | Create HTML form for context and question input | 5 | Adrash | feature/ui-form | To Do
QA-4 | Story | BERT Model Integration | Load fine-tuned BERT model using HuggingFace | 8 | Pawan Sharma | feature/bert-integration | To Do
QA-5 | Story | Tokenization Module | Implement BERT tokenizer preprocessing | 5 | Pawan Sharma | feature/tokenizer | To Do
QA-6 | Story | Prediction Endpoint | Create /predict POST API endpoint | 5 | Adrash | feature/api-predict | To Do
QA-7 | Story | Answer Extraction Logic | Extract answer span from model output | 8 | Rahul Singh | feature/answer-extraction | To Do
QA-8 | Story | Display Answer in UI | Show predicted answer on frontend | 3 | Sneha Verma | feature/ui-answer-display | To Do
QA-9 | Story | Logging System | Store user queries and answers in database | 5 | Pawan Sharma | feature/logging | To Do
QA-10 | Story | Error Handling | Handle empty input and runtime errors | 3 | Amit Kumar | feature/error-handling | To Do
QA-11 | Story | Health Check API | Implement /health endpoint | 2 | Amit Kumar | feature/health-api | To Do
QA-12 | Story | Gunicorn Configuration | Configure Gunicorn for production | 3 | Pawan Sharma | feature/gunicorn-config | To Do
QA-13 | Story | Render Deployment Setup | Deploy app to Render cloud | 5 | Pawan Sharma | feature/render-deployment | To Do
QA-14 | Story | Performance Optimization | Optimize model loading and response time | 8 | Rahul Singh | feature/performance-optimization | To Do
QA-15 | Story | Testing & Validation | Unit and integration testing | 5 | Sneha Verma | feature/testing | To Do
73